## Timeline
TASK | TIMELINE
| W1 | W2 | W3 | W 4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
M1 | bar: TIMELINE W1
M2 | bar: TIMELINE W2
M3 | bar: TIMELINE W3
M4 | bar: TIMELINE W 4
M5 | bar: TIMELINE W5 to TIMELINE W6
M6 | bar: TIMELINE W6 to TIMELINE W7
M7 | bar: TIMELINE W7 to TIMELINE W9
M8 | bar: TIMELINE W10
M9 | bar: TIMELINE W10 to TIMELINE W13
M10 | bar: TIMELINE W13 to TIMELINE W14

## Tasks
TASK | NAME
M1 | Kick-off meeting
Select programming language
Understand what is Instrumentation and Profiling
M2 | Choose a system
M3 | Choose Workloads/ application scenarios
M4 | Instrument the System
Decide what to instrument
Decide how to instrument
Choose implement some independent variable to record with instrument result
M5 | Run
M6 | Correlation analysis
Clustering
M7 | Repeat
M8 | Clean up code
M9 | Write report
M10 | Prepare Presentation